## Sheet1
# | Activity | Owner | Status | ETA | Notes
1 | OFS (CRM) latest production solution deployment. Engineering Master data import | @Jaydeep Gaikwad | Complete | 2018-11-28 | https://dynxsandbox.crm5.dynamics.com
Installed all necessary pre-requisites and latest OFS solutions.
Redesigned integration DLL with new approach of authentication, to avoid MFA issue.
2 | OFS (CRM) end to end smoke test after latest solution deployment | @Karthik N Krishnamurthi | Complete | 2018-11-30 | Completed OFS application testing successfully.
| Create Well master records |  |  |  | Pending integration testing
3 | Deploy VM on 7.3 PU20 (with Microsoft demo data) | @Satish Dalal | Complete | 2018-11-21 | https://infydevboxcdevaos.sandbox.ax.dynamics.com/
4 | Procure and deploy EAM license package from To-Increase | @Satish Dalal | Complete | 2018-11-21
5 | Identify list of hotfixes, binary updates, DLLs, model files to be deployed. | @Satish Dalal | Complete | 2018-11-21
6 | Extract and deploy hotfixes, binary updates, DLLs and model files | @Satish Dalal | Complete | 2018-11-22
7 | Strip codebase of Avalara code | @Satish Dalal | Complete | 2018-11-23
8 | Ensure environment compiles successfully | @Satish Dalal | Complete | 2018-11-26 | AX Environment setup is completed successfully.
9 | Setup companies with config and master data | @Parth Patel | Complete | 2018-11-29 | Master data is set.
Waiting for integration to be in place to start batch jobs.
10 | Configure integration with CRM | @Satish Dalal | In progress | 2018-11-30 | Shared integration DLL and Key into separate email.
Identified issue with Integration, it was with AX legal entity configuration. @Parth Patel is working on configuration fixes on AX environment. ETA is 2 days.
11 | Check for BJ specific content and remove if any -AX (for eg:- remove all BJ labels, or replace BJ names with Infosys, make sure there is no BJ specific master data as well) | @Satish Dalal | To be Started | 2018-11-27
12 | Check for BJ specific content and remove if any -CRM (for eg:- remove all BJ labels, or replace BJ names with Infosys, make sure there is no BJ specific master data as well) | @Sumi Srinivasan | In progress | 2018-11-30 | Allocated 2 CRM dev resources for OFS redesign.
|  | @Prateek Rahul |  |  | OFS application KT is in progress
Redesign tasks breakdown and finalization is in progress
13 | OFS(CRM) to AX end to end smoke testing | @Prateek Rahul | Depending on #10 | 2018-11-30
@Sumi Srinivasan
@Parth Patel
14 | Horizontal non BJ specific Solution development and maintenance -CRM | @Jaydeep Gaikwad | TBD | TBD | Strategy and schedule to keep this environment up to date. Best option is to have solution completely client agnostic and make solution completely configurable – TBD
Determine % of CRM to be reworked for removing client related information and estimate the effort involved accordingly
15 | Horizontal non BJ specific Solution | @Vijay Lad | TBD | TBD | Strategy and schedule to keep this environment up to date. Best option is to have solution completely client agnostic and make solution completely configurable – TBD
| Development and maintenance – AX | @Sarthak
Determine % of AX to be reworked for removing client related information and estimate the effort involved accordingly
16 | MS CRM upgrade to 9.0 | @Jaydeep Ashok Gaikwad | To be Started | 2018-12-21 | MS CRM online instances will be mandatory upgraded to 9.0 in January. It is difficult with MS CRM to maintain 2 version of application scripts (upgrade and redesign). So before starting any work in redesign, we will do basic minimum fixes for upgrade on dev environment and then we will start with redesign.
We will work with CCD to upgrade environment to 9.0 and then we will deploy 9.0 fixes and start with re-design tasks.